## Open Parking Lot Items
Issue No. | Status | Standard | Description | Assignment | Assigned To | Meeting Date Due | Discussion/Determination
12 | Open | 2.2 | Standards language needs to address the classification of interchange transactions that will be curtailed when unclear if a constrained facility or constrained flowgate is on a particular contract path | Provide draft language for consideration | A. Watkins | 2025-08-13 | 6/17/2025 - Discussed need for additional examples during meeting
12 | Open | 2.2 | Standards language needs to address the classification of interchange transactions that will be curtailed when unclear if a constrained facility or constrained flowgate is on a particular contract path | Provide additional information on how seams/congestion agreements are addressed by Eastern Interconnection/IDC | J. West | 2025-08-13
14 | Open | 1.4.1 & 1.4.2 | Revise standards language to capture intent to use e-Tag priority and actual real-time output | Develop revised language | A. Watkins | 2025-08-13
15 | Open | 1.4.2 | Evaluate entirety of section to determine if language needed or should be revised. | Provide additional information on how IDC/PFV uses real-time telemetry of a source/resource | J. West | 2025-08-13
16 | Open | 1.6.2 | Reformat the standard so similar requirements are grouped together (combine 1.4.1 and 1.6.2) | Develop revised language | A. Watkins | 2025-08-13
17 | Open | 2.2 & 2.3 | Revise language to remove "on-path/off-path" language | Develop revised language | A. Watkins | 2025-08-13

## Closed Parking Lot Items
Issue No. | Status | Standard | Description | Assignment | Assigned To | Meeting Date Due | Discussion/Determination
6 | Completed | 3.3 | Develop additional language for inclusion in 3.3 to clarify that relief obligations are made on a pro-rata basis by priority bucket | Draft initial language for consideration | A. Watkins | 2025-04-16 | 4/16/2025 - WG reviewed the revised language for 3.3.2.1 and determined that no additional changes are needed at this time
2 | Closed | 1.5 | Establishment of rules for prioritization of generation-to-load (Methods to Submit Intra-BA Transactions to the ECC) | Draft initial language for consideration | A. Watkins | 2025-05-16 | 4/16/2025 - Draft language will be provided in advance of the next meeting for review and discussion 5/17/2025 - Language reviewed during meeting
3 | Closed | 1.7.1 | Additional discussion and education on 1.7.1 Credit for Redispatch | Provide presentation on process used by the Eastern Interconnection | R. Thappetaobula | 2025-05-16 | 5/16/2025 - Presentation reviewed during meeting
4 | Closed | 1.7.2 | Add additional language to clarify the data used | Provide update on development of functional specification | A. Watkins | 2025-05-16 | 4/16/25 - Participants discussed that this could be better addressed through a functional specification that could provide the technical details of information exchange requirements 5/16/17 - Working Group agreed to close item, this is something that relates to the technical implementation of tool functionality
9 | Closed | 1.3 and 1.3.1 | Determine if ECC will provide log similar to TLR log in IDC and revise Access to WERL Logs if needed |  |  | 2025-05-16 | 4/16/2025 - Participants discussed that this action item can be addressed with Action Item 8
11 | Closed | 000-2 | Develop definitions for new defined terms (Market Area, Production Network Model, WELR, WELR Transaction Deadline) | Provide draft language for consideration | A. Watkins | 2025-05-16 | 5/16/2025 - Participants reviewed draft language
3 | Closed | 1.7.1 | Standards language needs to ensure that the credit for redsipatch methodology is sufficiently detailed to support implementation |  |  |  | 6/17/25 - WG closed issue; simplified by default consideration of firm for GTL
5 | Closed | 1.8 | Develop initial language to establish rules for consolidating BAAs into Market Areas (Consolidating of BAAs) | Draft initial language for consideration | A. Watkins | 2025-05-16 | 4/16/25 - Draft language will be provided in advance of the next meeting for review and discussion 5/17/2025 - Draft language reviewed; XXX-1.8 Consolidating BAAs struck and added XXX-1.6.3 to allow GTL relief obligations to be implemented by BA or BA delegation to Market Operator
7 | Closed | 3.3.2.4 | Develop additional language for 3.3.2.4 to sufficiently outline how intra-hour tags are handled | Provide additional revisions | A. Watkins | 2025-06-17 | 4/16/2025 - WG reviewed the revised language and discussed the need for further clarity to more closely mirror how UFMP addresses intra-hour curtailments 6/17/26 - Draft language reviewed during meeting
7 | Closed | 3.3.2.4 | Develop additional language for 3.3.2.4 to sufficiently outline how intra-hour tags are handled | Provide documentation regarding BPA business practices that address intra-hour tags | R. Chung | 2025-06-17
8 | Closed | 3.1 and 3.5 | Revise language to include notification for event start/end to entities beyond RCs, including BAs and transmisison service providers | Develop further revisions to provide additional details and clarity | A. Watkins | 2025-06-17 | 4/16/2025 - Participants reviewed the revised language and discussed the need for additional clarity regarding what information is to be provided as part of the notices and and to which entities 6/17/2025 - Draft language reviewed during meeting
8 | Closed | 3.1 and 3.5 | Revise language to include notification for event start/end to entities beyond RCs, including BAs and transmisison service providers | Develop draft language proposal for discussion | R. Hundal | 2025-06-17 | 6/17/2025 - Draft langauge reviewed during meeting
8 | Closed | 3.1 and 3.5 | Revise language to include notification for event start/end to entities beyond RCs, including BAs and transmisison service providers | Provide example of current ECC UFMP notices avaiable to merchants | J. West | 2025-06-17
10 | Closed | 1.5.1.1 | Determine if revisions are needed to Initial BA Declaration |  |  |  | 4/16/2025 - Participants discussed that this is an area which will need additional feedback from industry participants 6/17/2025 - Section deleted during meeting
13 | Closed | 2.4 | Additional clarity is needed on the WELR reallcoation and sub-priorities | Provide additional information at the next meeting in this area | A. Watkins | 2025-06-17 | 6/17/2025 - Section deleted during meeting
1 | Closed |  | Impact and obligations to Canadian entities. Is there a need to specifically address requirements applicable to these entities? | Provide feedback in this area for the next meeting regarding existing language | R. Hundal | 2025-08-07 | 8/7/2025 - No issues raised to-date with current draft; BC RC will provide additional comments if necessary
12 | Closed | 2.2 | Standards language needs to address the classification of interchange transactions that will be curtailed when unclear if a constrained facility or constrained flowgate is on a particular contract path | Provide examples for discussion at the next meeting regarding on-path/off-path determinations for the same priority level with jointly owned transmission facilities | R. Thappetaobula | 2025-08-07 | 6/17/2025 - Discussed need for additional examples during meeting 8/7/2025 - Examples have been discussed; revisions being addressed as part of Action Item 17