|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3g (2018) | 3e (2019) |  | 1 | Closed | Completed | Look at the scope of the project | A Shintani (BPA) | OS: 08/2018 | OS: 11/2018 | OS: 11/2018 | will address in November |
| 3g (2018) | 3e (2019) | 3a (2020) | 2 | Closed | Completed | To draft templates for the following:  Application Rollover DNR Rollover DNR Request | P Sorenson (OATI) | OS: 11/2018 | OS: 01/2019 | OS: 01/2020 |  |
| 3g (2018) | 3e (2019) |  | 3 | Closed | Completed | To review the document “Summary of Questions for NITS rollover” for further discussion on the topic of NITS rollover | Subcommittee members | OS: 02/2019 | OS: 05/2019 | OS: 05/2019 | 05/2019 reviewed document and answered all questions |
|  | 3e (2019) |  | 4 | Closed | Completed | To review the document “2019 API 3c&3e Parking Lot” for further discussion on the topic of NITS rollover and what can be marked as resolved and what needs to be worked on | Subcommittee members | OS: 05/2019 | OS: 06/2019 | OS: 06/2019 | Will closed this item out as 3c & 3e have been split apart. Will develop a new action item for the individual pieces. |
|  | 3e (2019) | 3a (2020) | 5 | Closed | Completed | To look at the standards for “registering items in OASIS/EIR” | K. Quimby | OS: 10/2019 | OS: 02/2020 | OS: 02/2020 | Changes will be included in the 2020 AP 3a. |
|  | 3e (2019) | 3a (2020) | 6 | Closed | Completed | To review WEQ-013 for NITS rollover |  | OS: 10/2019 |  | OS: 01/2020 | Will be addressed in assignment 8 |
|  | 3e (2019) | 3a (2020) | 7 | Closed | Completed | To review WEQ-003 for NITS rollover |  | OS: 10/2019 | OS: 01/2020 |  |  |
|  |  | 3a (2020) | 8 | Open | In Progress | To draft wording for NITS rollover in WEQ-013. | P Sorenson | OS: 01/2020 | OS: 03/2020 |  |  |
|  |  | 3a (2020) | 9 | Closed | Completed | To change wording for the indefinite termination for rollover rights | P Sorenson | OS: 01/2020 | OS: 02/2020 | OS: 01/2020 |  |
|  |  | 3a (2020) | 10 | Closed | Completed | Change 002-6 & 002-6.1 for next version | P Sorenson | OS: 01/2020 | OS: 01/2020 | OS: 01/2020 |  |
|  |  | 3a (2020) | 11 | Closed | Completed | Look to see if Summary of Questions for NITS Rollover complete | Members | OS: 01/2020 | OS: 01/2020 | OS: 01/2020 |  |