## 2018 API 3d&3g Parking Lot
Issue or Requirement covered by a Motion | WEQ Standard Changed / Added | Parking Lot Issue | Options | FERC Citation | Issue Comment | Resolved | Not Resolved | Future Work
Minor corrections
|  | Issue 1) 3/27-28/18 Minor corrections for all errata in WEQ-002; template errors, conflicting or incorrect Data Element names and cross-references, etc. |  | Example FERC Citation | 11/27-29/18 Completed | x
Minor OASIS Issues (Technical modifications only)
|  | Issue 1) 3/27-28/18 Evaluate all NITS Templates for changes in Data Element usage (required vs. optional), additional modifiable Data Elements, and update WEQ-001 as needed to align. Example: SUMMER_FORECAST, WINTER_FORECAST and FORECAST. Allow comment fields to be updated after confirmation. |  | Example FERC Citation | 11/27-29/18 Completed - Evaluate all NITS Templates for changes in Data Element usage (required vs. optional), 11/27-29/18 TBD - additional modifiable Data Elements, 11/27-29/18 completed - update WEQ-001 as needed to align. Example: SUMMER_FORECAST, WINTER_FORECAST and FORECAST. 11/27-29/18 completed - Allow comment fields to be updated after confirmation. 06/26/19 Matt S. will take this as an action item |  | x
|  | Issue 2) 3/27-28/18 Allow for Scheduling Rights (SRs) to use POR/Source and POD/Sink points that do not match the DNR or NITS Load service points. |  |  | 11/27-29/18 Completed | x
|  | Issue 3) 3/27-28/18 Allow customers to explicitly release SRs as part of a Terminate DNR request (include SR templates in TerminateNITSDNR). |  |  | 11/27-29/18 Completed | x
|  | Issue 4) 3/27-28/18 Remove DUNS number from the query parameters for the NITS templates. All Templates? |  |  | 11/27-29/18 Paul S will take an action item to complete. 06/27/19 Completed Subcommittee agreed that there will be no change to the standards at this time and keep as is. | x
|  | Issue 5) 3/27-28/18 Validation for termination requests to not allow a termination of capacity greater than that designated. |  |  | 11/27-29/18 Completed | x
|  | Issue 6) 3/27-28/18 Allow any generator as confirmed DNR for multiple loads. Do not permit the scheduling rights to exceed the generator capacity even though the sum of the individual DNRs exceeds the generator capacity. |  |  | 3/27-28/18 Duke Energy SEPA example (one off system generator declared in full capacity as a PPA DNR for mutiple Network Customers) 11/27-29/18 TBD will talk about this in more detail at a later date. Is this a NAESB issue? Can this be addressed thru some mapping mechanism? 06/26/19 Scott L. will take this as an action item 06/27/19 Completed Subcommittee and Duke Energy(Scott L.) agreed that this is not a NAESB issue and will close out this item. | x
|  | Issue 7) 3/27-28/18 The addition of the Transmission Customer name in the DNR list. 11/27-29/18 (different than CUSTOMER_CODE). Consider the addition of application name. |  |  | 11/27-29/18 Paul will put forth a proposal in for next meeting. 06/26/19 completed added APPLICATION_NAME to the DNR list but did not add CUSTOMER_NAME | x
|  | Issue 8) 3/27-28/18 Review the Application query templates for changes to improve information presented to Customers. |  |  | 11/27-29/18 TBD will addessed at a later date. This might add the DNR list to the application query. 11/27-29/18 Subcommittee supports adding the NITSDNRLIST to the query nits application. 06/27/19 Paul will take a look at this |  | x
|  | Issue 9) 8/22-23/18 Look at putting list on certain query responses (e.g., NITSLoadForecast, etc.) |  |  | 11/27-29/18 TBD everyone needs to look at 03/28/19 Paul will take back to look at |  | x
Issue 10)
Major OASIS Issues (BPS & Technical modifications)
|  | Issue 1) 3/27-28/18 Evaluate adding timing requirements associated with DEFICIENT requests. Applicable to all requests or just specific subset of requests? |  | Example FERC Citation | 06/26/19 Completed Subcomiittee made the determination that this item be closed to not add timing requirements. | x
|  | Issue 2) 3/27-28/18 Restriction that NITS Application cannot be ACCEPTED/CONFIRMED if any of original queued requests are still pending. Should this be relaxed such that the TP can leave some portions of the Application in STUDY condition while proceeding to approve an interim service agreement? |  |  | 06/26/19 competed 001-103.5.2.4 NITS requests may be left in STUDY if they require further evaluation and the Transmission Provider elects to proceed to grant the NITS Application prior to completing those STUDY requests | x
|  | Issue 3) 3/27-28/18 Should Load Forecast remain optional on OASIS? |  |  | 3/27-28/18 Subcommittee made the determination that the Load Forecast will remain optional on OASIS. | x
|  | Issue 4) 3/27-28/18 Is there a need for TP to be able to document any MW limitation on serving total load(s) as firm under the NITS Application at specific POD/Sink locations? This would be outside the scope of a load forecast (customer driven). |  |  | 06/26/19 looks to be complicated will keep on the list for future enhancements |  |  | x
|  | Issue 5) 3/27-28/18 Add support for fractional MW values to generation attributes? If supported, how far should fractional MW support be extended within the NITS model? Included in Load/Resource Forecasts? Others? |  |  | 06/26/19 completed Subcommittee will limit this item to just fractional MW/VAR values to deal with generator attributes (MWs and VARs only) | x
|  | Issue 6) 3/27-28/18 Need for expanding concept of generation groups? E.g., hierarchical groups - fleet, plant, unit (Nevada Power) |  |  | 06/26/19 looks to be complicated will keep on the list for future enhancements |  |  | x
|  | Issue 7) 3/27-28/18 Add requirement to enumerate the specific generation asset(s) associated with a GENERATION Resource at the time the Resource is declared? This would allow validation of appropriate use of the generation asset(s) in a DNR request. |  |  | 06/26/19 Subcommittee will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
|  | Issue 8) 3/27-28/18 Add ability to annul a Generation record. |  |  | 07/16/19 Subcommittee will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
|  | Issue 9) 3/27-28/18 Should optional nature be removed to require creating/posting of Scheduling Rights (SRs) whether requested by the customer or generated by the TP? |  |  | 07/16/19 Subcommittee will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
|  | Issue 10) 3/27-28/18 Should support to request/release SRs be added outside of the scope of a DNR request (standalone)? |  |  | 07/16/19 Subcommittee will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
|  | Issue 11) 3/27-28/18 Should SRs be associated with the addition of NITS Load? |  |  | 07/16/19 Subcommittee will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
Issue 12) 07/16/19 Moved to parking lot for 3e NITS rollover
Issue 13) 07/16/19 Moved to parking lot for 3e NITS rollover
Issue 14) 07/16/19 Moved to parking lot for 3e NITS rollover
|  | Issue 15) 3/27-28/18 Should WEQ-001 be updated to identify if/when DNRs are eligible for rollover rights? |  |  | 07/16/19 duplicate of issue 14
|  | Issue 16) 3/27-28/18 To remove requirement for EIR registration for full requirements Network Customers |  |  | 07/16/19 Mike S & Ken Q will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
|  | Issue 17) 3/27-28/18 Simultaneous Submission Windows (SSW) for NITS |  |  | 07/16/19 Subcommittee will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
|  | Issue 18) 11/27-29/18 Implementation ran into problems on how to handle a situation where a network load/generation has an effective stop time that has now passed, so the load/resource is basically dead. Should a new add/modify request be allowed that would start/stop in the future such that there would be a gap in time where the load/generation effectively did not exist? Should this be explicitly blocked and only way to get the load/generation back under the application is to give it a new load/generation name? |  |  | 07/16/19 Subcommittee will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
|  | Issue 19) 11/27-29/18 002-101.3.3.8 There have been some suggestions to all modification of other Resource attributes. What data elements have caused issues because they could not be modified, and are there any serious repercussions if there are modified while in use. Can the repercussions be mitigated by requirements stating under what conditions they can be modified? |  |  | 07/16/19 Subcommittee will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
|  | Issue 20) 11/27-29/18 a place where either a template or a file upload to accomdate a planned maintence schedule for generators and for load metering points |  |  | 07/16/19 Marlyn F will take this as an action item for the 07/23-25/19 meeting in Carmel |  | x
Added (not yet determined minor or major) OASIS Issues (BPS & Technical modifications)
|  | Issue 1) 8/22-23/18 Look at the timing of the deficiency status. |  |  | 11/27-29/18 this has been move and included in issue 1 of the major category | x
|  | Issue 2) 8/22-23/18 Implementation ran into problems on how to handle a situation where a network load/generation has an effective stop time that has now passed, so the load/resource is basically dead. Should a new add/modify request be allowed that would start/stop in the future such that there would be a gap in time where the load/generation effectively did not exist? Should this be explicitly blocked and only way to get the load/generation back under the application is to give it a new load/generation name? |  |  | 11/27-29/18 this has been moved and included as major issue 18 | x
|  | Issue 3) 8/22-23/18 See comment under ModifyNITSLoad with regard to potential termination of the load/generation and then subsequently resurrecting the named load/generation. |  |  | 11/27-29/18 this is a duplicate issue as in added issue 2 and major issue 18 and will be delt with in major issue 18 | x
|  | Issue 4) 8/22-23/18 002-101.3.3.8 There have been some suggestions to all modification of other Resource attributes. What data elements have caused issues because they could not be modified, and are there any serious repercussions if there are modified while in use. Can the repercussions be mitigated by requirements stating under what conditions they can be modified? |  |  | 11/27-29/18 this has been moved and included as major issue 19 | x
|  | Issue 5) 8/22-23/18 002-101.3.3.8 Should this be done. Had some issues where to set new effective stop time, user had to enter the original effective start which is way in the past. Begs question about submitting requests that start in the past. |  |  | 11/27-29/18 The subcommittee decided not to do this. | x
|  | Issue 6) 8/22-23/18 There have been some suggestions to not allow this and have attempts to terminate greater than what is designated. This was mainly for INDEFINITE_TERMINATION which takes on a single MW value to apply from effective start to forever. We could rethink handling of INDEFINITE_TERMINATION. |  |  | 11/27-29/18 - this has been completed in the recommendation | x
|  | Issue 7) 8/22-23/18 Look at putting list on certain query responses (e.g., NITSLoadForecast, etc.) |  |  | 11/27-29/18 this has been moved and included as minor issue 9 | x
|  | Issue 8) 8/22-23/18 Look at EFECTIVE_STOP_TIME and EFFECTIVE_START_TIME |  |  | 11/27-29/18 completed | x
|  | Issue 9) 8/22-23/18 Look at Table 105-A timing 11/27-29/18 specifcally look at deficent time limits |  |  | 11/27-29/18 completed as dupilcate of major issue 1 | x
|  | Issue 10) 11/27-29/18 a place where either a template or a file upload to accomdate a planned maintence schedule for generators and for load metering points |  |  | 11/27-29/18 this has been moved and included as major issue 20 | x
Issue 11) 07/16/19 Moved to parking lot for 3e NITS rollover
Issue 12) 07/16/19 Moved to parking lot for 3e NITS rollover
Issue 13) 07/16/19 Moved to parking lot for 3e NITS rollover
Issue 14) 07/16/19 Moved to parking lot for 3e NITS rollover
Not resolved
Resolved

## "Categories" List (hidden)
Categorization of 4/12/12 Preemption & Competition Parking Lot
Issues and Requirements | Definition of terms (including Defender and Challenger) | OASIS Subcommittee process/scope for Preemption & Competition | Conditionality / Conditional Window / Conditional statuses | Timing (Timing issues and Timing Table) | Matching requirements / Defender requirements and options | Displacement requirements | Challenger requirements | Interruptions | Redirects | Resales | Scheduling impacts | Duration vs. Effective Duration and cost vs price | Coordinated request for competition | Auditablity | Gaming | Simultaneous request | Multiple Defenders | Customer notification | Market impacts | SAMTS | Implementation Plan and Organization of BPs
Issue 1) 1/25-26/12 Row 2 of table 4-3 provides for a pending short term firm and confirmed short term firm can be preempted by a long term firm and native load and network firm which can be subsequently withdrawn thereby causing a potential gaming. Importance TP TC Ranking | x | [13 empty] | x |  |  |  | x
Issue 1.1. Changing the word “request” to “reservation” in table 4-3 column identifying the preempting request/reservation might solve the problem | x
Issue 1.2. Consider the name of the table 4-3 might need to be changed to described the table better for the purpose of this table | x
Issue 1.3. Consider changing the description of the table to describe requests and reservations | x
Issue 1.4. Need address the table 4-3 and all aspects of | x
Issue 2) 1/25-26/12 Add to the standards that the Customer would not require the request to be submitted pre-confirmed. The TP will require that the request be confirm before considering preemption/displacement of the reservation. | [5 empty] | x | x | [7 empty] | x |  |  |  | x
Issue 2.1. Keep in mind that there might be a tie breaker aspect of pre-confirmation. | [14 empty] | x |  |  |  | x
Issue 2.2. Discuss the pre-confirmation aspects of SAMTS (Pete has a power point for discussion) | [19 empty] | x
Issue 3) 2/9/12 Where to put this in the NAESB Business Practice Standards. | [20 empty] | x
Issue 4) 2/9/12 The matching request does not have a shorter duration than the product type. E.g. this shows up when a daily reservation is matching a weekly request. | [11 empty] | x
Issue 5) 2/9/12 Business practices should specify exactly what constitutes a “matching” request with regard to term, service, and capacity necessary to retain transmission service rights |  |  |  |  | x
Issue 5.1. are the terms of the matching request set by the Transmission Provider and/or can the duration, capacity , or price be changed by the Transmission Customer |  |  |  |  | x | [11 empty] | x
Issue 5.2. define how the matching profiles extensions are built when the defender has zero MW segments |  |  |  |  | x | [6 empty] | x
Issue 6) 2/9/12 Need to look at definitions of DISPLACE and SUPERSEDE to make sure that these still apply. | x
Issue 7) 2/9/12 Look and define conditionality rules more clear. Also look at timing table to make sure that the conditionalities are not violated. | x |  | x | x
Issue 7.1. right of first refusal |  |  |  | x | x | [11 empty] | x
Issue 7.2. customer confirmation time limit and the conditionality need be coordinated (both the challenger and the defender) |  |  | x | x |  |  | x
Issue 8) 2/9/12 Need to look at pre-confirmation of the challengers request. | [6 empty] | x
Issue 9) 2/9/12 Need to look at retaining the pre-confirmation priority order of a counteroffer challenge |  |  |  |  | x | x | [12 empty] | x
Issue 10) 2/9/12 must account for displacement of service in-whole or in-part |  |  |  |  | x | x
Issue 10.1. if part of the defenders capacity is needed what is the resulting combination matching reservation capacity and the remaining capacity on the defender reservation? May these be combined in the matching request so that only one reservation remains at the end of the preemption process? |  |  |  |  | x
Issue 10.2. if part of the capacity is needed and the defender chooses not to match, should he loose all the original reservation, only the part needed by the challenger, or does he have a choice? | [5 empty] | x
Issue 11) 2/9/12 Business Practices must address both Firm and Non-Firm Point-to-Point and Network transmission services. |  | x | x |  | x |  | x
Issue 11.1. Response time to submit matching requests for non-firm ptp |  |  |  | x | x
Issue 11.2. Define conditionality for non-firm ptp, secondary network, and redirects on a non-firm basis |  |  | x
Issue 11.3. Clarify the need for determine the capacity in the challenger’s request that can be profiled and used for challenging | [6 empty] | x |  |  |  |  | x
Issue 11.4. Competition for path vs competition for flowgate capacity. Do the challenger and defender have a common path component or can defenders be selected from reservations which have capacity on a constraining flowgate? If flowgate based, can a matching request be required for greater MWs than the challenger based on the relative distribution factor? Should the challenger and defender have the same flowgates? |  |  |  |  | x |  | x
Issue 11.5. Competition for capacity by multiple defenders (when not all defenders can be accommodated). |  |  |  |  | x | [9 empty] | x |  | x | x
Issue 11.6. ROFR treatment for challenges to RENEWAL requests and challenges to reservations with rollover rights (long term). Cluster studies and ROFR |  |  | x |  | x | [13 empty] | x
Issue 11.7. Should competition address MWh to initiate competition and rank defenders? |  |  |  |  | x |  | x |  |  |  |  | x
Issue 12) 2/9/12 Need to look at pre-confirmation of the matching request. |  |  |  |  | x
Issue 13) 2/9/12 Must minimize the potential for any “gaming” opportunities between competing customers | [14 empty] | x |  |  |  | x
Issue 13.1. Confirm the challenger at the beginning of competition as a form of conditional confirmation (e.g. subject to recall upon defender exercising ROFR). | [6 empty] | x | [7 empty] | x |  |  | x | x
Issue 13.1.a) The challenger shall not be permitted to redirect or resell the confirmed capacity while the preemption process is still going on. | [6 empty] | x |  | x | x
Issue 13.1.b) What is the fair treatment for modifying a confirmed request (challenger). This might require setting up a new state (e.g PROVISIONALLY CONFIRMED) with timing guidelines. | x |  |  | x |  | x | x | [7 empty] | x |  |  | x
Issue 13.2. The defender shall not redirect or resell to retain their capacity after being identified as subject to preemption. |  |  |  |  | x |  |  |  | x | x |  |  |  |  | x |  |  | x
Issue 13.3. Should full service (ROFR not exercised) be required in order to consider a Transmission Service Request as a valid challenger? With this there would be no need for counteroffer to the challenger. | [6 empty] | x
Issue 13.3.a) Discuss the implication on defenders without ROFR when another defender has exercised ROFR. |  |  |  | x |  | x
Issue 13.4. Counteroffer when partial service is available – must it be flat profile? | [5 empty] | x | x
Issue 14) 2/9/12 Make sure that we comply with FERC Order 638 |  | x
Issue 14.1. Alan will document this
Issue 15) 2/9/12 Make sure that standard considers FERC Order 890.
Issue 16) 2/9/12 Discuss the reference simultaneous request allocation method. (890-A p. 802-806) | [15 empty] | x
Issue 16.1. Provisional Item 2 2012 NAESB AP Develop business practices for allocating capacity among requests received during a submittal window Order 890-A (Docket Nos. RM05-17-001, 002 and RM05-25-001, 002 - Paragraph 805) | [15 empty] | x
Requirement 1) 2/9/12 …to minimize the potential for gaming, a preempting longer request must be for a fixed capacity over the term of the request. (890 p. 1436) Subcommittee comment: | [6 empty] | x | [7 empty] | x
Requirement 2) 2/9/12 …when a longer-term request seeks capacity allocated to multiple shorter term requests, the shorter-term customers should have simultaneous opportunities to exercise the right of first refusal. Duration, pre-confirmation status, price, and time of response would then be used to determine which of the shorter term requests will be able to exercise the right of first refusal, consistent with the Commission’s tie breaking provision in section 13.2(ii)…. (890 p. 1436) Subcommittee comment: |  |  |  | x | x | [11 empty] | x
Requirement 2.a. Does this mean if there is enough capacity for one to excerise ROFR and not all, do you challenge all or just one. |  |  |  |  | x | [11 empty] | x
Requirement 3) 2/9/12 …section 13.2(iii)…“Before the conditional reservation deadline, if available transfer capability is insufficient to satisfy all Applications, an Eligible Customer with a reservation for shorter term service has the right of first refusal to match any longer term request before losing its reservation priority”… (890 p. 1437) Subcommittee comment: “Defender = Reservation Challenger = Request” | x |  | x | x | x
Requirement 4) 2/9/12 The Commission affirms the decision in Order No. 890 to give priority based on pre-confirmed status only to short-term firm and long-term non-firm requests for service…. (890-A p. 786) Subcommittee comment: |  |  |  |  | x |  | x
Requirement 5) 2/9/12 …in the event an offer for service on a pre-confirmed request can only be accommodated by additions to the transmission provider’s transmission system, the transmission customer may: (1) take a shorter term of service, if available; (2) agree to undertake any upgrades that may be necessary to accommodated the transmission requests; or (3) decline service…. (890-A p. 787) Subcommittee comment: Pre-confirmation cannot be withdrawn. | [6 empty] | x | [10 empty] | x
Requirement 6) 2/9/12 …in order for a competing request of equal price to preempt a reservation for three conservative days of daily service, that request must be for four consecutive days or longer and must be received at least one day before the first day of the original customer’s three-day term of service. (890-A p 789) Subcommittee comment: Challenger request has to be longer than Defender and of equal price. Also the term of the defender will be considered in its entirety not pieces. |  |  | x | x |  |  | x
Requirement 7) 2/9/12 …The Commission has revised those sections of the pro forma OATT to more accurately reflect our intent that pre-confirmation service should be available to all eligible customers seeking short-term firm and non-firm transmission services. (890-A p. 790) Subcommittee comment: For pre-confirmation request all customers (Eligible and Transmission) will get priority. |  |  | x |  |  | x
Requirement 8) 2/9/12 …section 13.2 of the pro forma OATT, price serves as a tie-breaker among competing service requests of equal duration only when the transmission provider has offered a discount or a “below ceiling rate” on transmission service. Transmission providers may not charge rates above those stated in their OATT for primary transmission capacity. (890-A p. 793) Subcommittee comment: |  |  |  |  | x | x | [10 empty] | x
Requirement 9) 2/9/12 …denies rehearing of the Commission’s decision in Order No. 890 to require transmission providers that have adopted a “no earlier than” time for submitting requests for firm transmission service to treat all requests received within a specified period of time as having been received simultaneously…. (890-A p, 802) Subcommittee comment: There may be a requirement that will state that if the “no earlier than” method is used there will be a Transmission Provider Business Practice. | [15 empty] | x
Requirement 10) 2/9/12 …In the off-chance that multiple eligible customers with short-term reservations choose to exercise their right of first refusal for the same capacity simultaneously, the Commission believes that they should have a right to do so. (890-A p.815) …As noted above, we recognize that certain unique cases can present difficult allocation issues, but conclude that these extreme cases arise infrequently in the normal course of business. In the vast majority of cases, we believe the right of first refusal rules are efficient and easy to administer without further amending the governing tariff language… (890-A p. 816) Subcommittee comment: We will discuss and determine if the subcommittee will address this issue. See 890-B p. 161. |  | x | [14 empty] | x
Requirement 11) 2/9/12 …that a “competing request” under sections 13.2 and 14.2 of the pro forma OATT may include a transmission service request that overlaps with only part of another existing transmission service reservation since both requests cannot be granted simultaneously. Accordingly, a “competing request” for purposes of sections 13.2 and 14.2 may also include a transmission service request for which transmission capacity cannot be accommodated without preempting one or more existing transmission reservations of parts thereof. (890-A p. 817) Subcommittee comment: |  |  |  |  | x |  | x | [9 empty] | x
Requirement 12) 2/9/12 …we clarify that sections 13.2 and 14.2 allow an eligible customer to retain its original reservation by matching the competing service request’s cost or duration terms exactly or by exceeding one or more of the terms of a competing transmission service request. Since any “match” by an eligible customer in response to a potentially preempting request, by definition, either exceeds the costs, duration or both of the eligible customer’s original reservation, we do not believe eligible customers opting to match a competing request have a strong incentive, if any, to “match” a competing request with terms that exceed the competing request. Nevertheless, we do not see any harm resulting from a match that exceeds the exact terms of a competing request and therefore believe it would not be appropriate to preclude the ability of eligible customers to make such a request. (890-A p. 818) Subcommittee comment: May look at cost being price and MWs. Need to review tariff language carefully. |  |  |  |  | x
Requirement 13) 2/9/12 With regard to reassignments of capacity in the secondary market, we clarify that the associated right of first refusal under sections 13.2 and 14.2 of the pro forma OATT to match a competing transmission service request applies to the primary transmission service, not the reassignment of scheduling rights…. The fact that one day of service has been reassigned does not alter the assignor’s entitlement to use service for the remaining week reserved. (890-A p. 819) Subcommittee comment: We need to look at this very carefully with who is the Defender and what happens to the reassignment. Also look at partial reassignments and which portion of the original reservation is preempted. |  |  |  |  | x |  |  |  |  | x
Requirement 14) 2/22/12 Consider delinking redirects from resales for preemption and competition. i.e. Linking the redirect away from the resales and linking it back to the original parent reservation.
Requirement 15) 2/22/12 Consider disallowing redirects of resales. This not viewed favorably by BPA market participants. | [8 empty] | x | x | [8 empty] | x
Requirement 16) 2/22/12 Consider limiting resales only to the unconditional window of the parent. This not viewed favorably by BPA market participants. |  |  | x | [6 empty] | x | [8 empty] | x
Requirement 17) 2/22/12 Consider resales are not defenders per order 890-A p. 819. However if the parent does or does not defend then resales will be affected. |  |  |  |  | x | x |  |  |  | x
Requirement 18) 2/22/12 Consider resales from multiple reservations that have been aggregated into one reservation. What to do about this situation. |  |  | x |  | x | x |  |  |  | x | [6 empty] | x
Requirement 19) 2/22/12 Consider redirects of an aggregated reservation what to do when more than one of the aggregation is subject to preemption and competition. | [8 empty] | x
Requirement 20) 2/22/12 Who is an valid defender |  |  |  |  | x
Requirement 20.a. Identical por\pod |  |  |  |  | x
Requirement 20.b. Identical source\sink |  |  |  |  | x
Requirement 20.c. Must mitigate atc/afc deficit |  |  |  |  | x
Requirement 20.d. Comparable treatment regardless of atc methodology |  |  |  |  | x
Requirement 20.e. Defender must improve the offer of the challenger |  |  |  |  | x
Requirement 21) 2/22/12 Consider effective duration (start/stop time) vs request start/stop time interval. (e.g. 24 hourly profile with zero on the peak periods and non-zero on the off peak times) | [11 empty] | x
Requirement 22) 2/22/12 How many defenders? |  |  |  |  | x | [11 empty] | x
Requirement 22.a. Minimum number of defenders who, if all failed to defend, would provide sufficient ATC for a full offer to the challenger. |  |  |  |  | x | [11 empty] | x
Requirement 22.b. More defenders available than needed in Option a |  |  |  |  | x | [11 empty] | x
Requirement 22.b.i. How many more or maximum? |  |  |  |  | x | [11 empty] | x
Requirement 22.b.ii. A fixed number? |  |  |  |  | x | [11 empty] | x
Requirement 22.b.iii. A percentage of valid defenders? |  |  |  |  | x | [11 empty] | x
Requirement 23) 2/22/12 Look at matching per order 890 p 818 make sure that we include in standard |  |  |  |  | x
Requirement 24) 2/22/12 Consider Pre-submittal Workspace to queue a valid matching request. |  | x
Requirement 25) 2/23/12 if the initial competition is complete, and there is still not enough capacity to grant a full offer to the challenger, should the TP reevaluate the queue to find additional defenders? | [16 empty] | x
Requirement 26) 2/23/12 Do we need a different state to handle challengers request prior to defenders/competition completed? Maybe look at CR_ACCEPTED as the mechanism for handling this. | x |  | x |  |  | x | [12 empty] | x
Requirement 27) 2/23/12 Look at requiring preconfirmation for challengers/defenders for competition in the short term time frame. | [6 empty] | x
Requirement 28) 2/23/12 Look at short term first(13.2 & 14.2 of Tariff) and then look at long term(tier 1 2.2 of Tariff). Subcommittee comment: decided on looking at short term first |  | x
Requirement 29) 2/23/12 Look at timing deadline of firm and non-firm of defenders match |  |  |  | x | x
Requirement 30) 2/23/12 Consider if the challenge is looked at for matching and the match cannot be allowed from a study perspective what will happen to the challenger? Defender? |  |  |  | x | x |  | x
Requirement 31) 2/23/12 Look at if the challenger is feasible prior to | [6 empty] | x
Requirement 32) 2/23/12 Defender has moved into unconditional window before the deadline to response to the competition. |  |  | x | x | x
Requirement 33) 2/23/12 Defender may have submitted tags against their TSR prior to their response window closing, or the tagging window may open before the defender is required to submit their response. | [10 empty] | x
Requirement 34) 4/5/12 Look at table 4.3 line 3a-c should the pending request for short term be pre-empted by longer duration without ROFR. | [5 empty] | x
Requirement 35) 4/5/12 Look at table 4.3 line 4 should this be expanded or explanation to include duration of term. | x
Requirement 36) 4/5/12 look at redirect and resales on an hourly basis, should there be preemption and competition? | [8 empty] | x | x | [8 empty] | x
Requirement 36.a. 4/10/12 Look at the loss of the value of the resale (SNPD) | [9 empty] | x | [8 empty] | x
Requirement 36.b. 4/10/12 Look at the liquidity of the resale and how the market will react (Seattle) | [9 empty] | x | [8 empty] | x
Requirement 36.c. 4/10/12 Look at possible liquidated damages because of loss of firm transmission service (Tacoma) | [18 empty] | x
Requirement 37) 4/10/12 Limiting competition to new(original not redirect) requests only (TEA) |  |  |  |  | x |  | x |  | x | x
Requirement 38) 4/10/12 Limiting competition to weekly requests or longer (TEA) | [6 empty] | x | [11 empty] | x
Requirement 39) 4/10/12 Look at timing of the competition (on when & How it will be cut off) |  |  |  | x |  | x
Requirement 39.a. 4/11/12 Look at scheduling requirements | [5 empty] | x |  |  |  |  | x | [7 empty] | x
Requirement 40) 4/10/12 Impact on PTP load serving entities (TEA) | [18 empty] | x
Requirement 41) 4/10/12 Impact on NT load serving entities (TEA) | [18 empty] | x
Requirement 42) 4/10/12 Market impact (TEA) | [18 empty] | x
Requirement 43) 4/10/12 Specific impact (TEA) | [18 empty] | x
Requirement 43.a. Short-term competition will impact DA and RT scheduling process | [10 empty] | x | [7 empty] | x
Requirement 43.b. Short-term competition will impact IT systems |  |  |  | x
Requirement 44) 4/10/12 Look at potential market abuse (SNPD) | [14 empty] | x
Requirement 45) 4/10/12 Native load vs customer load how to differentiate the two for competition (SNPD) | x |  |  |  | x |  | x
Requirement 46) 4/10/12 Different implications depending on ATC methodology (SNPD) |  |  |  |  | x | x | x
Requirement 47) 4/10/12 Generation only entity, how will competition affect them. | [18 empty] | x
Requirement 48) 4/10/12 Look at the standards of redirect on a firm basis does this impact the competition and does it need to be looked at and redefined. | [8 empty] | x
Requirement 49) 4/10/12 Look at the possibility of continuing the parents reservation (conditionality) attributes to the redirected child and maybe the possibility the attributes of the resales. |  |  | x |  |  |  | x |  | x | x
Requirement 49.a. Should consider whether or not the redirect can or cannot be a challenger with this attribute |  |  | x |  |  |  | x |  | x
Requirement 50) 4/10/12 Look at can a challenger invoke ROFR if there is zero atc on the path and there is no capacity for the defender to match. |  |  |  |  | x
Requirement 50.a. Can a defender be identified based on priority if there is no capacity to match |  |  |  |  | x
Requirement 50.b. Or stop the competition |  |  |  |  | x
Requirement 50.c. Or something else |  |  |  |  | x
Requirement 51) 4/10/12 Does there have to be sufficient capacity for ALL defenders to match? |  |  |  |  | x | [11 empty] | x
Requirement 51.a. All defenders that are identified have to match |  |  |  |  | x | [11 empty] | x
Requirement 51.b. Only one based on capacity |  |  |  |  | x | [11 empty] | x
Requirement 51.c. Or something else |  |  |  |  | x | [11 empty] | x
Requirement 52) 4/10/12 How many rounds of competition should take place? |  |  |  |  | x | x
Requirement 53) 4/10/12 How should tags be managed if the related TSR loses its capacity? | [10 empty] | x | [6 empty] | x
Requirement 54) 4/10/12 Would it be preferable to have the matching request created automatically? |  |  |  |  | x | [12 empty] | x | x
Requirement 55) 4/10/12 Would it be preferable to change both the start and end dates of a TSR when matching? |  |  |  |  | x | [5 empty] | x
Requirement 56) 4/10/12 What is the minimum capacity (MW) required to match a challenging request? |  |  |  |  | x
Requirement 57) 4/10/12 Should competitions take place if a full offer to the challenger is not possible? |  |  |  |  | x | x | x
Requirement 57.a. Challenger Declaring a minimum MW threshold. |  |  |  |  | x | x | x
Requirement 57.b. Challenger offered the counteroffer amount of capacity prior to competition |  |  |  |  | x | x | x
Requirement 57.c. Challenger has the option to not compete | [6 empty] | x
Requirement 58) 4/11/12 Discuss the timeline for testing and implementation of the project | [20 empty] | x
Requirement 59) 4/11/12 Dynamic tags, Block schedules, Pseudo, etc. need to be looked at and discussed |  |  |  |  | x | [5 empty] | x
Requirement 59.a. Not competeable? |  |  |  |  | x | [5 empty] | x
Requirement 59.b. What to do with tags and reservations |  |  |  |  | x | [5 empty] | x
Requirement 60) 4/11/12 auditablity need to look at the requirements to make sure that all is covered for an audit | [13 empty] | x
Requirement 61) 4/11/12 alarms and notifications need to look at to see if we need to implement | [17 empty] | x
Requirement 62) 4/11/12 Coordinated Requests for Competition: should there be a feature that returns a defending reservation their original granted characteristics (duration, MW, price, etc.) that it lost due to not matching a competition, when the challenger fails to confirm a Counter-offer. |  |  |  |  | x | x | x
Requirement 63) 4/11/12 Make sure that SAMTS is included in the evaluation of preemption | [12 empty] | x | [6 empty] | x
Requirement 64) 4/11/12Look at transparency issues | [13 empty] | x
Requirement 65) 4/11/12 Look at an “opt out” flag for challenger | [6 empty] | x
Requirement 66) 4/11/12 Look at exemption oneself out of competition for not competing against oneself. | [6 empty] | x | [11 empty] | x
Requirement 67) 4/11/12 What is the nature of a valid matching request with respect to capacity and duration? |  |  |  |  | x
Requirement 67.a. Min and max MW discussion |  |  |  |  | x
Requirement 67.b. What happens if they do something that is not allowed under a TP tariff |  |  |  |  | x
Requirement 67.c. Profiling issues (weekly with daily profiles) |  |  |  |  | x
Requirement 67.d. Duration extensions (weekly match when only three days needed) |  |  |  |  | x
Requirement 67.e. Elevating part of the original defender reservation to higher service (one day 50MW only 5MW needed to match- weekly profile with 50MW first day and 5 the remaining) |  |  |  |  | x
Requirement 68) 4/11/12 Expand the requirements needed on how to create a matching request |  |  |  |  | x | [12 empty] | x
Requirement 68.a. How does the challenger notify the defender and TP that a matching is occurring |  |  |  |  | x |  | x | [10 empty] | x
Requirement 68.b. What information needs to be provided |  |  |  |  | x |  | x | [10 empty] | x
Requirement 69) 4/11/12 Look at blocking/allowing leading, lagging, and intervening zeros on an request. |  |  |  |  | x |  | x | [7 empty] | x |  |  |  | x
Requirement 69.a. How should daily on peak and daily off peak be handled in competition |  |  |  |  | x |  | x | [7 empty] | x |  |  |  | x
Requirement 69.b. How should extended products be handled in competition |  |  |  |  | x |  | x
Requirement 69.c. How is duration defined | x |  |  |  | x |  | x
Requirement 70) 4/11/12 Simultaneous Matching Feasibility |  |  |  |  | x | [11 empty] | x
Requirement 70.a. Longer duration request preempts multiple shorter duration requests, the shorter duration requests shall have simultaneous opportunities to exercise the right of first refusal. |  |  |  |  | x | [11 empty] | x
Requirement 70.b. Question do you skip a lower priority defender that cannot match a challenger. |  |  |  |  | x | [11 empty] | x
Requirement 71) 4/11/12 Competition to Make Counteroffer |  |  |  |  | x | [11 empty] | x
Requirement 71.a. Confirmed vs non-confirmed requests |  |  |  |  | x | [11 empty] | x
Requirement 72) 4/11/12 if queue tie are considered equal what is the tie breaker to determine defender priority.(simultaneous submission window) |  |  |  |  | x | [10 empty] | x
Requirement 73) 4/11/12 Look at the firm priority over non-firm to move the displacement of non-firm from current to the scheduling deadline. | [5 empty] | x
Requirement 74) 4/11/12 Look at the timing table for secondary non-firm ptp. |  |  | x | x
Requirement 74.a. Do we need to address conditionality |  |  | x | x
Requirement 74.b. Dealing with preemption row 9 tier 5 of table 4.3 |  |  | x | x
Requirement 75) 4/11/12 Do we need to specify conditionality of the non-firms based on duration. |  |  | x
Requirement 76) 4/11/12 NERC standard (729) |  | x
Requirement 76.a. MOD |  | x
Requirement 76.b. INT(2008-12) |  | x

## Combined list (hidden)
Preemption and Competition Parking lot Issues and Requirements Identified by Category
Issues and Requirements | Definition of terms (including Defender and Challenger) | OASIS Subcommittee process/scope for Preemption & Competition | Conditionality / Conditional Window / Conditional statuses | Timing (Timing issues and Timing Table) | Matching requirements / Defender requirements and options | Displacement requirements | Challenger requirements | Interruptions | Redirects | Resales | Scheduling impacts | Duration vs. Effective Duration and cost vs price | Coordinated request for competition | Auditablity | Gaming | Simultaneous request | Multiple Defenders | Customer notification | Market impacts | SAMTS | Implementation Plan and Organization of BPs | What constitutes duration? | What constitutes qualifications for valid defender? | What constitutes a valid competition? | What is the ROFR process, including timing? | Treatment of RESALEs | Treatment of REDIRECTs | Treatment of tags using displaced transmission | What is the scope of the NAESB process and how should it be organized?
Issue 1) 1/25-26/12 Row 2 of table 4-3 provides for a pending short term firm and confirmed short term firm can be preempted by a long term firm and native load and network firm which can be subsequently withdrawn thereby causing a potential gaming. Importance TP TC Ranking | x | [13 empty] | x |  |  |  | x | [5 empty] | x
Issue 1.1. Changing the word “request” to “reservation” in table 4-3 column identifying the preempting request/reservation might solve the problem | x | [23 empty] | x
Issue 1.2. Consider the name of the table 4-3 might need to be changed to described the table better for the purpose of this table | x | [23 empty] | x
Issue 1.3. Consider changing the description of the table to describe requests and reservations | x | [23 empty] | x
Issue 1.4. Need address the table 4-3 and all aspects of | x | [23 empty] | x
Issue 2) 1/25-26/12 Add to the standards that the Customer would not require the request to be submitted pre-confirmed. The TP will require that the request be confirm before considering preemption/displacement of the reservation. | [5 empty] | x | x | [7 empty] | x |  |  |  | x |  |  |  |  | x
Issue 2.1. Keep in mind that there might be a tie breaker aspect of pre-confirmation. | [14 empty] | x |  |  |  | x |  |  |  |  | x
Issue 2.2. Discuss the pre-confirmation aspects of SAMTS (Pete has a power point for discussion) | [19 empty] | x |  |  |  | x
Issue 3) 2/9/12 Where to put this in the NAESB Business Practice Standards. | [20 empty] | x | [7 empty] | x
Issue 4) 2/9/12 The matching request does not have a shorter duration than the product type. E.g. this shows up when a daily reservation is matching a weekly request. | [11 empty] | x | [9 empty] | x
Issue 5) 2/9/12 Business practices should specify exactly what constitutes a “matching” request with regard to term, service, and capacity necessary to retain transmission service rights |  |  |  |  | x | [19 empty] | x
Issue 5.1. are the terms of the matching request set by the Transmission Provider and/or can the duration, capacity , or price be changed by the Transmission Customer |  |  |  |  | x | [11 empty] | x | [7 empty] | x
Issue 5.2. define how the matching profiles extensions are built when the defender has zero MW segments |  |  |  |  | x | [6 empty] | x | [12 empty] | x
Issue 6) 2/9/12 Need to look at definitions of DISPLACE and SUPERSEDE to make sure that these still apply. | x | [23 empty] | x
Issue 7) 2/9/12 Look and define conditionality rules more clear. Also look at timing table to make sure that the conditionalities are not violated. | x |  | x | x | [19 empty] | x | x
Issue 7.1. right of first refusal |  |  |  | x | x | [11 empty] | x | [7 empty] | x
Issue 7.2. customer confirmation time limit and the conditionality need be coordinated (both the challenger and the defender) |  |  | x | x |  |  | x | [17 empty] | x
Issue 8) 2/9/12 Need to look at pre-confirmation of the challengers request. | [6 empty] | x | [16 empty] | x
Issue 9) 2/9/12 Need to look at retaining the pre-confirmation priority order of a counteroffer challenge |  |  |  |  | x | x | [12 empty] | x | [5 empty] | x
Issue 10) 2/9/12 must account for displacement of service in-whole or in-part |  |  |  |  | x | x | [17 empty] | x | x
Issue 10.1. if part of the defenders capacity is needed what is the resulting combination matching reservation capacity and the remaining capacity on the defender reservation? May these be combined in the matching request so that only one reservation remains at the end of the preemption process? |  |  |  |  | x | [19 empty] | x
Issue 10.2. if part of the capacity is needed and the defender chooses not to match, should he loose all the original reservation, only the part needed by the challenger, or does he have a choice? | [5 empty] | x | [17 empty] | x
Issue 11) 2/9/12 Business Practices must address both Firm and Non-Firm Point-to-Point and Network transmission services. |  | x | x |  | x |  | x | [21 empty] | x
Issue 11.1. Response time to submit matching requests for non-firm ptp |  |  |  | x | x | [19 empty] | x
Issue 11.2. Define conditionality for non-firm ptp, secondary network, and redirects on a non-firm basis |  |  | x | [20 empty] | x
Issue 11.3. Clarify the need for determine the capacity in the challenger’s request that can be profiled and used for challenging | [6 empty] | x |  |  |  |  | x | [11 empty] | x
Issue 11.4. Competition for path vs competition for flowgate capacity. Do the challenger and defender have a common path component or can defenders be selected from reservations which have capacity on a constraining flowgate? If flowgate based, can a matching request be required for greater MWs than the challenger based on the relative distribution factor? Should the challenger and defender have the same flowgates? |  |  |  |  | x |  | x | [16 empty] | x
Issue 11.5. Competition for capacity by multiple defenders (when not all defenders can be accommodated). |  |  |  |  | x | [9 empty] | x |  | x | x |  |  |  |  | x
Issue 11.6. ROFR treatment for challenges to RENEWAL requests and challenges to reservations with rollover rights (long term). Cluster studies and ROFR |  |  | x |  | x | [13 empty] | x | [5 empty] | x |  |  |  | x
Issue 11.7. Should competition address MWh to initiate competition and rank defenders? |  |  |  |  | x |  | x |  |  |  |  | x | [11 empty] | x
Issue 12) 2/9/12 Need to look at pre-confirmation of the matching request. |  |  |  |  | x | [19 empty] | x
Issue 13) 2/9/12 Must minimize the potential for any “gaming” opportunities between competing customers | [14 empty] | x |  |  |  | x | [5 empty] | x
Issue 13.1. Confirm the challenger at the beginning of competition as a form of conditional confirmation (e.g. subject to recall upon defender exercising ROFR). | [6 empty] | x | [7 empty] | x |  |  | x | x | [5 empty] | x |  |  |  | x
Issue 13.1.a) The challenger shall not be permitted to redirect or resell the confirmed capacity while the preemption process is still going on. | [6 empty] | x |  | x | x | [14 empty] | x
Issue 13.1.b) What is the fair treatment for modifying a confirmed request (challenger). This might require setting up a new state (e.g PROVISIONALLY CONFIRMED) with timing guidelines. | x |  |  | x |  | x | x | [7 empty] | x |  |  | x | [6 empty] | x
Issue 13.2. The defender shall not redirect or resell to retain their capacity after being identified as subject to preemption. |  |  |  |  | x |  |  |  | x | x |  |  |  |  | x |  |  | x | [7 empty] | x | x
Issue 13.3. Should full service (ROFR not exercised) be required in order to consider a Transmission Service Request as a valid challenger? With this there would be no need for counteroffer to the challenger. | [6 empty] | x | [16 empty] | x
Issue 13.3.a) Discuss the implication on defenders without ROFR when another defender has exercised ROFR. |  |  |  | x |  | x | [18 empty] | x
Issue 13.4. Counteroffer when partial service is available – must it be flat profile? | [5 empty] | x | x | [17 empty] | x
Issue 14) 2/9/12 Make sure that we comply with FERC Order 638 |  | x | [21 empty] | x
Issue 14.1. Alan will document this | [28 empty] | x
Issue 15) 2/9/12 Make sure that standard considers FERC Order 890. | [29 empty] | n/a
Issue 16) 2/9/12 Discuss the reference simultaneous request allocation method. (890-A p. 802-806) | [15 empty] | x | [13 empty] | n/a
Issue 16.1. Provisional Item 2 2012 NAESB AP Develop business practices for allocating capacity among requests received during a submittal window Order 890-A (Docket Nos. RM05-17-001, 002 and RM05-25-001, 002 - Paragraph 805) | [15 empty] | x | [12 empty] | x
Requirement 1) 2/9/12 …to minimize the potential for gaming, a preempting longer request must be for a fixed capacity over the term of the request. (890 p. 1436) Subcommittee comment: | [6 empty] | x | [7 empty] | x | [6 empty] | x
Requirement 2) 2/9/12 …when a longer-term request seeks capacity allocated to multiple shorter term requests, the shorter-term customers should have simultaneous opportunities to exercise the right of first refusal. Duration, pre-confirmation status, price, and time of response would then be used to determine which of the shorter term requests will be able to exercise the right of first refusal, consistent with the Commission’s tie breaking provision in section 13.2(ii)…. (890 p. 1436) Subcommittee comment: |  |  |  | x | x | [11 empty] | x | [6 empty] | x | x
Requirement 2.a. Does this mean if there is enough capacity for one to excerise ROFR and not all, do you challenge all or just one. |  |  |  |  | x | [11 empty] | x | [6 empty] | x
Requirement 3) 2/9/12 …section 13.2(iii)…“Before the conditional reservation deadline, if available transfer capability is insufficient to satisfy all Applications, an Eligible Customer with a reservation for shorter term service has the right of first refusal to match any longer term request before losing its reservation priority”… (890 p. 1437) Subcommittee comment: “Defender = Reservation Challenger = Request” | x |  | x | x | x | [17 empty] | x
Requirement 4) 2/9/12 The Commission affirms the decision in Order No. 890 to give priority based on pre-confirmed status only to short-term firm and long-term non-firm requests for service…. (890-A p. 786) Subcommittee comment: |  |  |  |  | x |  | x | [16 empty] | x | x
Requirement 5) 2/9/12 …in the event an offer for service on a pre-confirmed request can only be accommodated by additions to the transmission provider’s transmission system, the transmission customer may: (1) take a shorter term of service, if available; (2) agree to undertake any upgrades that may be necessary to accommodated the transmission requests; or (3) decline service…. (890-A p. 787) Subcommittee comment: Pre-confirmation cannot be withdrawn. | [6 empty] | x | [10 empty] | x
Requirement 6) 2/9/12 …in order for a competing request of equal price to preempt a reservation for three conservative days of daily service, that request must be for four consecutive days or longer and must be received at least one day before the first day of the original customer’s three-day term of service. (890-A p 789) Subcommittee comment: Challenger request has to be longer than Defender and of equal price. Also the term of the defender will be considered in its entirety not pieces. |  |  | x | x |  |  | x | [14 empty] | x
Requirement 7) 2/9/12 …The Commission has revised those sections of the pro forma OATT to more accurately reflect our intent that pre-confirmation service should be available to all eligible customers seeking short-term firm and non-firm transmission services. (890-A p. 790) Subcommittee comment: For pre-confirmation request all customers (Eligible and Transmission) will get priority. |  |  | x |  |  | x | [18 empty] | x
Requirement 8) 2/9/12 …section 13.2 of the pro forma OATT, price serves as a tie-breaker among competing service requests of equal duration only when the transmission provider has offered a discount or a “below ceiling rate” on transmission service. Transmission providers may not charge rates above those stated in their OATT for primary transmission capacity. (890-A p. 793) Subcommittee comment: |  |  |  |  | x | x | [10 empty] | x | [7 empty] | x
Requirement 9) 2/9/12 …denies rehearing of the Commission’s decision in Order No. 890 to require transmission providers that have adopted a “no earlier than” time for submitting requests for firm transmission service to treat all requests received within a specified period of time as having been received simultaneously…. (890-A p, 802) Subcommittee comment: There may be a requirement that will state that if the “no earlier than” method is used there will be a Transmission Provider Business Practice. | [15 empty] | x | [12 empty] | x
Requirement 10) 2/9/12 …In the off-chance that multiple eligible customers with short-term reservations choose to exercise their right of first refusal for the same capacity simultaneously, the Commission believes that they should have a right to do so. (890-A p.815) …As noted above, we recognize that certain unique cases can present difficult allocation issues, but conclude that these extreme cases arise infrequently in the normal course of business. In the vast majority of cases, we believe the right of first refusal rules are efficient and easy to administer without further amending the governing tariff language… (890-A p. 816) Subcommittee comment: We will discuss and determine if the subcommittee will address this issue. See 890-B p. 161. |  | x | [14 empty] | x
Requirement 11) 2/9/12 …that a “competing request” under sections 13.2 and 14.2 of the pro forma OATT may include a transmission service request that overlaps with only part of another existing transmission service reservation since both requests cannot be granted simultaneously. Accordingly, a “competing request” for purposes of sections 13.2 and 14.2 may also include a transmission service request for which transmission capacity cannot be accommodated without preempting one or more existing transmission reservations of parts thereof. (890-A p. 817) Subcommittee comment: |  |  |  |  | x |  | x | [9 empty] | x
Requirement 12) 2/9/12 …we clarify that sections 13.2 and 14.2 allow an eligible customer to retain its original reservation by matching the competing service request’s cost or duration terms exactly or by exceeding one or more of the terms of a competing transmission service request. Since any “match” by an eligible customer in response to a potentially preempting request, by definition, either exceeds the costs, duration or both of the eligible customer’s original reservation, we do not believe eligible customers opting to match a competing request have a strong incentive, if any, to “match” a competing request with terms that exceed the competing request. Nevertheless, we do not see any harm resulting from a match that exceeds the exact terms of a competing request and therefore believe it would not be appropriate to preclude the ability of eligible customers to make such a request. (890-A p. 818) Subcommittee comment: May look at cost being price and MWs. Need to review tariff language carefully. |  |  |  |  | x | [18 empty] | x | x
Requirement 13) 2/9/12 With regard to reassignments of capacity in the secondary market, we clarify that the associated right of first refusal under sections 13.2 and 14.2 of the pro forma OATT to match a competing transmission service request applies to the primary transmission service, not the reassignment of scheduling rights…. The fact that one day of service has been reassigned does not alter the assignor’s entitlement to use service for the remaining week reserved. (890-A p. 819) Subcommittee comment: We need to look at this very carefully with who is the Defender and what happens to the reassignment. Also look at partial reassignments and which portion of the original reservation is preempted. |  |  |  |  | x |  |  |  |  | x | [13 empty] | x |  | x
Requirement 14) 2/22/12 Consider delinking redirects from resales for preemption and competition. i.e. Linking the redirect away from the resales and linking it back to the original parent reservation. | [25 empty] | x | x
Requirement 15) 2/22/12 Consider disallowing redirects of resales. This not viewed favorably by BPA market participants. | [8 empty] | x | x | [8 empty] | x | [6 empty] | x | x
Requirement 16) 2/22/12 Consider limiting resales only to the unconditional window of the parent. This not viewed favorably by BPA market participants. |  |  | x | [6 empty] | x | [8 empty] | x | [6 empty] | x
Requirement 17) 2/22/12 Consider resales are not defenders per order 890-A p. 819. However if the parent does or does not defend then resales will be affected. |  |  |  |  | x | x |  |  |  | x | [12 empty] | x |  |  | x
Requirement 18) 2/22/12 Consider resales from multiple reservations that have been aggregated into one reservation. What to do about this situation. |  |  | x |  | x | x |  |  |  | x | [6 empty] | x | [8 empty] | x
Requirement 19) 2/22/12 Consider redirects of an aggregated reservation what to do when more than one of the aggregation is subject to preemption and competition. | [8 empty] | x | [17 empty] | x
Requirement 20) 2/22/12 Who is an valid defender |  |  |  |  | x | [17 empty] | x
Requirement 20.a. Identical por\pod |  |  |  |  | x | [17 empty] | x
Requirement 20.b. Identical source\sink |  |  |  |  | x | [17 empty] | x
Requirement 20.c. Must mitigate atc/afc deficit |  |  |  |  | x | [17 empty] | x
Requirement 20.d. Comparable treatment regardless of atc methodology |  |  |  |  | x | [17 empty] | x
Requirement 20.e. Defender must improve the offer of the challenger |  |  |  |  | x | [17 empty] | x
Requirement 21) 2/22/12 Consider effective duration (start/stop time) vs request start/stop time interval. (e.g. 24 hourly profile with zero on the peak periods and non-zero on the off peak times) | [11 empty] | x | [9 empty] | x
Requirement 22) 2/22/12 How many defenders? |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 22.a. Minimum number of defenders who, if all failed to defend, would provide sufficient ATC for a full offer to the challenger. |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 22.b. More defenders available than needed in Option a |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 22.b.i. How many more or maximum? |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 22.b.ii. A fixed number? |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 22.b.iii. A percentage of valid defenders? |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 23) 2/22/12 Look at matching per order 890 p 818 make sure that we include in standard |  |  |  |  | x | [19 empty] | x
Requirement 24) 2/22/12 Consider Pre-submittal Workspace to queue a valid matching request. |  | x | [22 empty] | x
Requirement 25) 2/23/12 if the initial competition is complete, and there is still not enough capacity to grant a full offer to the challenger, should the TP reevaluate the queue to find additional defenders? | [16 empty] | x | [7 empty] | x
Requirement 26) 2/23/12 Do we need a different state to handle challengers request prior to defenders/competition completed? Maybe look at CR_ACCEPTED as the mechanism for handling this. | x |  | x |  |  | x | [12 empty] | x | [5 empty] | x
Requirement 27) 2/23/12 Look at requiring preconfirmation for challengers/defenders for competition in the short term time frame. | [6 empty] | x | [16 empty] | x
Requirement 28) 2/23/12 Look at short term first(13.2 & 14.2 of Tariff) and then look at long term(tier 1 2.2 of Tariff). Subcommittee comment: decided on looking at short term first |  | x | [26 empty] | x
Requirement 29) 2/23/12 Look at timing deadline of firm and non-firm of defenders match |  |  |  | x | x | [19 empty] | x
Requirement 30) 2/23/12 Consider if the challenge is looked at for matching and the match cannot be allowed from a study perspective what will happen to the challenger? Defender? |  |  |  | x | x |  | x | [16 empty] | x
Requirement 31) 2/23/12 Look at if the challenger is feasible prior to | [6 empty] | x | [16 empty] | x
Requirement 32) 2/23/12 Defender has moved into unconditional window before the deadline to response to the competition. |  |  | x | x | x | [19 empty] | x
Requirement 33) 2/23/12 Defender may have submitted tags against their TSR prior to their response window closing, or the tagging window may open before the defender is required to submit their response. | [10 empty] | x | [16 empty] | x
Requirement 34) 4/5/12 Look at table 4.3 line 3a-c should the pending request for short term be pre-empted by longer duration without ROFR. | [5 empty] | x | [17 empty] | x
Requirement 35) 4/5/12 Look at table 4.3 line 4 should this be expanded or explanation to include duration of term. | x | [20 empty] | x
Requirement 36) 4/5/12 look at redirect and resales on an hourly basis, should there be preemption and competition? | [8 empty] | x | x | [8 empty] | x | [6 empty] | x | x
Requirement 36.a. 4/10/12 Look at the loss of the value of the resale (SNPD) | [9 empty] | x | [8 empty] | x | [6 empty] | x
Requirement 36.b. 4/10/12 Look at the liquidity of the resale and how the market will react (Seattle) | [9 empty] | x | [8 empty] | x | [6 empty] | x
Requirement 36.c. 4/10/12 Look at possible liquidated damages because of loss of firm transmission service (Tacoma) | [18 empty] | x | [9 empty] | x
Requirement 37) 4/10/12 Limiting competition to new(original not redirect) requests only (TEA) |  |  |  |  | x |  | x |  | x | x | [16 empty] | x
Requirement 38) 4/10/12 Limiting competition to weekly requests or longer (TEA) | [6 empty] | x | [11 empty] | x |  |  |  |  | x
Requirement 39) 4/10/12 Look at timing of the competition (on when & How it will be cut off) |  |  |  | x |  | x | [18 empty] | x
Requirement 39.a. 4/11/12 Look at scheduling requirements | [5 empty] | x |  |  |  |  | x | [7 empty] | x | [8 empty] | x
Requirement 40) 4/10/12 Impact on PTP load serving entities (TEA) | [18 empty] | x | [9 empty] | x
Requirement 41) 4/10/12 Impact on NT load serving entities (TEA) | [18 empty] | x | [9 empty] | x
Requirement 42) 4/10/12 Market impact (TEA) | [18 empty] | x | [9 empty] | x
Requirement 43) 4/10/12 Specific impact (TEA) | [18 empty] | x | [9 empty] | x
Requirement 43.a. Short-term competition will impact DA and RT scheduling process | [10 empty] | x | [7 empty] | x | [8 empty] | x
Requirement 43.b. Short-term competition will impact IT systems |  |  |  | x | [24 empty] | x
Requirement 44) 4/10/12 Look at potential market abuse (SNPD) | [14 empty] | x | [8 empty] | x
Requirement 45) 4/10/12 Native load vs customer load how to differentiate the two for competition (SNPD) | x |  |  |  | x |  | x | [17 empty] | x
Requirement 46) 4/10/12 Different implications depending on ATC methodology (SNPD) |  |  |  |  | x | x | x | [17 empty] | x |  |  |  | x
Requirement 47) 4/10/12 Generation only entity, how will competition affect them. | [18 empty] | x | [9 empty] | x
Requirement 48) 4/10/12 Look at the standards of redirect on a firm basis does this impact the competition and does it need to be looked at and redefined. | [8 empty] | x | [17 empty] | x
Requirement 49) 4/10/12 Look at the possibility of continuing the parents reservation (conditionality) attributes to the redirected child and maybe the possibility the attributes of the resales. |  |  | x |  |  |  | x |  | x | x | [15 empty] | x | x
Requirement 49.a. Should consider whether or not the redirect can or cannot be a challenger with this attribute |  |  | x |  |  |  | x |  | x | [17 empty] | x
Requirement 50) 4/10/12 Look at can a challenger invoke ROFR if there is zero atc on the path and there is no capacity for the defender to match. |  |  |  |  | x | [18 empty] | x
Requirement 50.a. Can a defender be identified based on priority if there is no capacity to match |  |  |  |  | x
Requirement 50.b. Or stop the competition |  |  |  |  | x | [17 empty] | x
Requirement 50.c. Or something else |  |  |  |  | x | [17 empty] | x
Requirement 51) 4/10/12 Does there have to be sufficient capacity for ALL defenders to match? |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 51.a. All defenders that are identified have to match |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 51.b. Only one based on capacity |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 51.c. Or something else |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 52) 4/10/12 How many rounds of competition should take place? |  |  |  |  | x | x | [18 empty] | x
Requirement 53) 4/10/12 How should tags be managed if the related TSR loses its capacity? | [10 empty] | x | [6 empty] | x | [9 empty] | x
Requirement 54) 4/10/12 Would it be preferable to have the matching request created automatically? |  |  |  |  | x | [12 empty] | x | x | [5 empty] | x
Requirement 55) 4/10/12 Would it be preferable to change both the start and end dates of a TSR when matching? |  |  |  |  | x | [5 empty] | x | [13 empty] | x
Requirement 56) 4/10/12 What is the minimum capacity (MW) required to match a challenging request? |  |  |  |  | x | [19 empty] | x
Requirement 57) 4/10/12 Should competitions take place if a full offer to the challenger is not possible? |  |  |  |  | x | x | x | [16 empty] | x
Requirement 57.a. Challenger Declaring a minimum MW threshold. |  |  |  |  | x | x | x | [16 empty] | x
Requirement 57.b. Challenger offered the counteroffer amount of capacity prior to competition |  |  |  |  | x | x | x | [16 empty] | x
Requirement 57.c. Challenger has the option to not compete | [6 empty] | x | [16 empty] | x
Requirement 58) 4/11/12 Discuss the timeline for testing and implementation of the project | [20 empty] | x | [7 empty] | x
Requirement 59) 4/11/12 Dynamic tags, Block schedules, Pseudo, etc. need to be looked at and discussed |  |  |  |  | x | [5 empty] | x | [16 empty] | x
Requirement 59.a. Not competeable? |  |  |  |  | x | [5 empty] | x | [16 empty] | x
Requirement 59.b. What to do with tags and reservations |  |  |  |  | x | [5 empty] | x | [16 empty] | x
Requirement 60) 4/11/12 auditablity need to look at the requirements to make sure that all is covered for an audit | [13 empty] | x | [14 empty] | x
Requirement 61) 4/11/12 alarms and notifications need to look at to see if we need to implement | [17 empty] | x | [6 empty] | x
Requirement 62) 4/11/12 Coordinated Requests for Competition: should there be a feature that returns a defending reservation their original granted characteristics (duration, MW, price, etc.) that it lost due to not matching a competition, when the challenger fails to confirm a Counter-offer. |  |  |  |  | x | x | x | [17 empty] | x
Requirement 63) 4/11/12 Make sure that SAMTS is included in the evaluation of preemption | [12 empty] | x | [6 empty] | x | [8 empty] | x
Requirement 64) 4/11/12Look at transparency issues | [13 empty] | x | [14 empty] | x
Requirement 65) 4/11/12 Look at an “opt out” flag for challenger | [6 empty] | x | [17 empty] | x
Requirement 66) 4/11/12 Look at exemption oneself out of competition for not competing against oneself. | [6 empty] | x | [11 empty] | x | [5 empty] | x
Requirement 67) 4/11/12 What is the nature of a valid matching request with respect to capacity and duration? |  |  |  |  | x | [16 empty] | x |  | x
Requirement 67.a. Min and max MW discussion |  |  |  |  | x | [18 empty] | x
Requirement 67.b. What happens if they do something that is not allowed under a TP tariff |  |  |  |  | x | [18 empty] | x
Requirement 67.c. Profiling issues (weekly with daily profiles) |  |  |  |  | x | [18 empty] | x
Requirement 67.d. Duration extensions (weekly match when only three days needed) |  |  |  |  | x | [18 empty] | x
Requirement 67.e. Elevating part of the original defender reservation to higher service (one day 50MW only 5MW needed to match- weekly profile with 50MW first day and 5 the remaining) |  |  |  |  | x | [19 empty] | x
Requirement 68) 4/11/12 Expand the requirements needed on how to create a matching request |  |  |  |  | x | [12 empty] | x | [6 empty] | x
Requirement 68.a. How does the challenger notify the defender and TP that a matching is occurring |  |  |  |  | x |  | x | [10 empty] | x | [6 empty] | x
Requirement 68.b. What information needs to be provided |  |  |  |  | x |  | x | [10 empty] | x | [6 empty] | x
Requirement 69) 4/11/12 Look at blocking/allowing leading, lagging, and intervening zeros on an request. |  |  |  |  | x |  | x | [7 empty] | x |  |  |  | x |  |  | x
Requirement 69.a. How should daily on peak and daily off peak be handled in competition |  |  |  |  | x |  | x | [7 empty] | x |  |  |  | x |  |  | x
Requirement 69.b. How should extended products be handled in competition |  |  |  |  | x |  | x | [14 empty] | x
Requirement 69.c. How is duration defined | x |  |  |  | x |  | x | [14 empty] | x
Requirement 70) 4/11/12 Simultaneous Matching Feasibility |  |  |  |  | x | [11 empty] | x | [6 empty] | x
Requirement 70.a. Longer duration request preempts multiple shorter duration requests, the shorter duration requests shall have simultaneous opportunities to exercise the right of first refusal. |  |  |  |  | x | [11 empty] | x | [6 empty] | x
Requirement 70.b. Question do you skip a lower priority defender that cannot match a challenger. |  |  |  |  | x | [11 empty] | x | [5 empty] | x
Requirement 71) 4/11/12 Competition to Make Counteroffer |  |  |  |  | x | [11 empty] | x | [7 empty] | x
Requirement 71.a. Confirmed vs non-confirmed requests |  |  |  |  | x | [11 empty] | x | [7 empty] | x
Requirement 72) 4/11/12 if queue tie are considered equal what is the tie breaker to determine defender priority.(simultaneous submission window) |  |  |  |  | x | [10 empty] | x | [12 empty] | x
Requirement 73) 4/11/12 Look at the firm priority over non-firm to move the displacement of non-firm from current to the scheduling deadline. | [5 empty] | x | [18 empty] | x
Requirement 74) 4/11/12 Look at the timing table for secondary non-firm ptp. |  |  | x | x | [20 empty] | x
Requirement 74.a. Do we need to address conditionality |  |  | x | x | [19 empty] | x
Requirement 74.b. Dealing with preemption row 9 tier 5 of table 4.3 |  |  | x | x | [19 empty] | x
Requirement 75) 4/11/12 Do we need to specify conditionality of the non-firms based on duration. |  |  | x | [20 empty] | x
Requirement 76) 4/11/12 NERC standard (729) |  | x | [26 empty] | x
Requirement 76.a. MOD |  | x | [26 empty] | x
Requirement 76.b. INT(2008-12) |  | x | [26 empty] | x

## 2018 API 3d&3g OASIS Motions
Motion | Date | Motion By | Second | Status | Motion | WEQ Standard Changed / Added | Issues and Requirements resolved | Assignments | ACTIVE | still valid/ concerns
1
2
3
4
5