## WEQ BPS
Business Practices Subcommittee Action Items
Issue # | Status | Description | Assigned to | Dates
| Open |  |  |  |  | Meeting
| Closed |  |  |  |  | When will
| Hold |  |  | Assigned | Due | be Addressed | Notes
Next Number to assign - 2

## OASIS Assignments
OASIS Subcommittee Action Items
API (year) | Issue # | Status (Open Closed Hold) | Progress (Completed Not Started In Progress) | Description | Assigned to | Dates |  |  | Notes
[6 empty] | Assigned | Due | When Addressed
3a (2018) | 1 | Closed | Completed | Outline the scope for Requirements for OASIS to use data in the Electric Industry Registry (R12001) | K Quimby (SPP) | OS: 11/2017 | OS: 2/2018 | OS: 2/2018
3b (2018) | 1 | Closed | Completed | Outline the scope for Evaluate the ability to define specific lists to submitted for the Query/Response in the OASIS Template format and develop new standards/modifications as needed | M Schingle (MISO) | OS: 1/2018 | OS: 2/2018 | OS: 2/2018
3c (2018) | 1 | Closed | Completed | Outline the scope for Evaluate adding dynamic notification for the rollover rights renewal deadline and develop new standards/modifications as needed | M Schingle (MISO) | OS: 1/2018 | OS: 2/2018 | OS: 2/2018
3d (2018) | 1 | Closed | Completed | Outline the scope for Review the NAESB Network Integration Transmission Service (NITS) Business and Technical Standards for needed modifications based on implementation and operational experiences since their adoption. See API for details | P Sorenson (OATI) | OS: 11/2017 | OS:3/2018 | OS:3/2018
3e (2018) | 1 | Closed | Completed | Outline the scope for Develop new OASIS Business Practice Standards to ensure that reservation capacity that is assigned to untagged Pseudo-Ties is preserved for that purpose. See API for details | A. Pritchard (Duke) [R Arbitelle (Southern)] | OS: 11/2017 | OS:1/2018 | OS:1/2018
3f (2018) | 1 | Open | In Progress | Outline the scope for Evaluate the need for new OASIS Business Practice Standards and/or mechanisms to allow documentation for coordination of partial path reservations to demonstrate the complete path associated with long-term firm interchange. This information, when populated, would provide a tool to improve coordination of interchange by transmission planners when developing planning models. This will provide greater certainty that partial path reservations are properly accounted for in transmission planning models and that reliable service is provided | J Manning (NCEMC) | OS: 11/2017 | OS:3/2018
3e (2018) | 2 | Closed | Completed | Develop an EIR Pseudo-Tie entry primer. | K Quimby (SPP) | OS: 01/2018 | OS: 02/2018 | OS: 02/2018
3a (2018) | 2 | Open | In Progress | Refine the scope for Requirements for OASIS to use data in the Electric Industry Registry (R12001) | K Quimby (SPP) | OS: 02/2018 | OS: 11/2018 |  | will be address in November
3a (2018) | 3 | Closed | Completed | Identify the data elements from WEQ-003 that have valid values {Registered}. | M Steigerwald (BPA) | OS: 02/2018 | OS: 3/2018 | OS: 3/2018
3b (2018) | 2 | Closed | Completed | Refine the scope for Evaluate the ability to define specific lists to submitted for the Query/Response in the OASIS Template format and develop new standards/modifications as needed | M Schingle (MISO) | OS: 2/2018 | OS: 3/2018 | OS:5/2018 | will be address in May
3c (2018) | 2 | Closed | Completed | Refine the scope for Evaluate adding dynamic notification for the rollover rights renewal deadline and develop new standards/modifications as needed | M Schingle (MISO) | OS: 1/2018 | OS: 3/2018 | OS:5/2018 | will be address in May also narrowed scope to PTP
3e (2018) | 3 | Closed | Completed | Refine the scope to aline with Option 3 for Develop new OASIS Business Practice Standards to ensure that reservation capacity that is assigned to untagged Pseudo-Ties is preserved for that purpose. See API for details | A. Pritchard (Duke) | OS: 2/2018 | OS:3/2018 | OS:3/2018
3d (2018) | 2 | Closed | Completed | Outline the scope for Minor corrections for all errata in WEQ-002; template errors, conflicting or incorrect Data Element names and cross-references, etc. | P Sorenson (OATI) | OS: 3/2018 | OS:4/2018 | OS:5/2018 | will continue to address in May
3b (2018) | 3 | Closed | Completed | Refine the scope and draft standard language for Evaluate the ability to define specific lists to submitted for the Query/Response in the OASIS Template format and develop new standards/modifications as needed | M Schingle (MISO) | OS: 3/2018 | OS: 5/2018 | OS:5/2018
3c (2018) | 3 | Closed | Completed | Refine the scope and draft standard language for Evaluate adding dynamic notification for the rollover rights renewal deadline and develop new standards/modifications as needed | M Schingle (MISO) | OS: 3/2018 | OS: 5/2018 | OS: 8/2018 | This was item was addressed in the May 2018 meeting and the discussion was extended to the July meeting
3e (2018) | 4 | Closed | Completed | Expand the scope for Developing a new OASIS Business Practice Standards to ensure that reservation capacity that is assigned to untagged Pseudo-Ties is preserved for that purpose. See API for details | A. Pritchard (Duke) | OS: 3/2018 | OS:4/2018 | OS:4/2018
3d (2018) | 3 | Closed | Completed | Review 002-101.3.2.9 & 002-101.3.2.11 get with their respective entities, reasearch, and return with a response to the subcommittee. | Subcommittee members | OS: 4/2018 | OS:5/2018 | OS:5/2018
3e (2018) | 5 | Closed | Completed | Develop draft standrds for Developing a new OASIS Business Practice Standards to ensure that reservation capacity that is assigned to untagged Pseudo-Ties is preserved for that purpose. See API for details | A. Pritchard (Duke) | OS: 4/2018 | OS:5/2018 | OS:5/2018
3e (2018) | 6 | Closed | Completed | Develop draft standrds for Developing a new OASIS Business Practice Standards to ensure that reservation capacity that is assigned to untagged Pseudo-Ties is preserved for that purpose for NITS. See API for details | JT Wood (SOCO) | OS: 5/2018 | OS:6/2018 | OS:6/2018
3e (2018) | 7 | Closed | Completed | Develop WEQ-002, 003 & 013 draft standrds for Developing a new OASIS Business Practice Standards to ensure that reservation capacity that is assigned to untagged Pseudo-Ties is preserved for that purpose for PTP. See API for details | A. Pritchard (Duke) | OS: 5/2018 | OS:6/2018 | OS:6/2018
3b (2018) | 4 | Closed | Completed | Develop a recommendation for Evaluate the ability to define specific lists to submitted for the Query/Response in the OASIS Template format and develop new standards/modifications as needed | M Schingle (MISO) | OS: 5/2018 | OS: 6/2018 | OS:6/2018
3d (2018) | 4 | Open | In Progress | Scope for scheduling rights for the West; Report back on standards WEQ-002-101.3.2.9 & 002-101.3.2.11 | P Sorenson (OATI) | OS: 5/2018 | OS:11/2018 |  | will continue to address in November
3e (2018) | 8 | Closed | Completed | look at the informal comments from the industry | industry | OS:6/2018 | OS:7/2018 | OS: 8/2018 | voted out for formal comment
3g (2018) | 1 | Open | In Progress | Look at the scope of the project | A Shintani (BPA) | OS: 8/2018 | OS:11/2018 |  | will address in November
3c (2018) | 4 | Closed | Completed | Look at the HTTP implementation to see if any entity uses this mechanism | P Sorenson (OATI) R Robinson (TVA) | OS: 9/2018 | OS: 10/2018 | OS: 10/2018
3c (2018) | 5 | Closed | Completed | To craft a strawman for dynamic notification for WEQ-002 and template structures for WEQ-002 | P Sorenson (OATI) | OS: 9/2018 | OS: 10/2018 | OS: 10/2018
3c (2018) | 6 | Closed | Completed | Draft a recommendation for 2018 API 3c | JT Wood (SOCO) | OS: 9/2018 | OS: 10/2018 | OS: 10/2018
3d/3g (2018) | 5 | Open | In Progress | Set up recommdnation for 3d/3g and hard redline the scope for minor corrections already talked about. | JT Wood (SOCO) | OS: 10/2018 | OS:11/2018
3c/3h (2018) | 7 | Open | In Progress | look at 3c/3h draft recommendation and make sure that the final actions for the versions do not include 3.3 in the titles of the OASIS books 000,001,002,003, and 013 | JT Wood (SOCO) | OS: 10/2018 | OS:11/2018

## BPS_OS Joint Open
Joint Business Practices Subcommittee and OASIS Action Items
Issue # | Status | Description | Assigned to | Dates
| Open |  |  |  |  | Meeting
| Closed |  |  |  |  | When will
| Hold |  |  | Assigned | Due | be Addressed | Notes

## Joint Closed
Joint Business Practices Subcommittee and OASIS Action Items
Issue # | Status | Description | Assigned to | Dates
| Open |  |  |  |  | Meeting
| Closed |  |  |  |  | When will
| Hold |  |  | Assigned | Due | be Addressed | Notes
1 | Closed | Review what information is available on the events and circumstances contributing to the curtailment of firm service and customers curtailed, including the transmission provider's own retail load and the duration of the curtailment (AP Item 2.a.ii.1) | BPS |  |  | 2016-06-07 | 10/6/15 - Created work paper but before finalizing need additional input from customers 6/7/16 - This item was completed through Action Item 11
2 | Closed | What information is needed to comply with FERC requirements for additional data postings for the benefit of customers and auditors. (AP Item 2.a.ii.1) | BPS |  |  | 2016-06-07 | 10/6/15 - Created work paper but before finalizing need additional input from customers 6/7/16 - This item was completed through Action Item 11
3 | Closed | What information is publically available in the IDC for the Eastern Interconnection and the USF (unscheduled flow) procedures in the WECC (AP Item 2.a.ii.1) | BPS |  |  | 2016-06-07 | 10/6/15 - IDC currently doesn't make information available publically. Also, IDC doesn't know the reason congestion is occuring 6/7/16 - This item was completed through Action Item 11
4 | Closed | What is meant by planning redispatch? Is it only long-term? Is it only firm? Etc. Order 890, Paragraph 901+ (AP Item 2.a.ii.2) | BPS |  |  |  | 12/1/15 - BPS determined that third party offers are for planning redispatch which is for long-term firm
5 | Closed | What information is needed from third parties for planning redispatch that will satisfy requirement for need for the transmission providers to implement congestion management (AP Item 2.a.ii.2) | BPS |  |  |  | 12/1/15 - BPS decided to post the generator information from third parties.
6 | Closed | How are third party offers for planning redispatch service acquired by customers? Off OASIS process? How will these arrangments be submitted to transmission providers for verification and validation? (AP Item 2.a.ii2) | BPS |  |  |  | 12/1/15 - BPS determined that third party offers are acquired by the customers of OASIS. Submission of third party offers to transmission providers will be based on the specific requirements of transmission providers
7 | Closed | Review R12006 and API 3.a.i.3 in order to identify any requirements that would be specific to SAMTS request by NITS customers (AP Item 5.e) | BPS/J. Manning |  | 2015-11-04 |  | 11/4 - New Action Item 12 created to identify any additional information
9 | Closed | What information is a transmission customer seeking on available generation dispatch options that will allow acceptance of the reservation request (AP Item 3.a.i.3) | BPS |  |  |  | 3/1/2016 - BPS agreed to forward work paper for review by OASIS Subcommittee
10 | Closed | Create a document for informal comment to solicit information on Action Items 4 - 6 | N. Saini | 2015-10-06 | 2015-12-01 | 2015-12-01 | 11/4 - Reviewed document prepared by Mr. Saini and BPS decided to further work on based on OATT requirements before posted for informal comment 12/1 - BPS decided to include generation information for third party offers for planning redispatch. No informal comments are needed.
11 | Closed | Create a document for informal comment to solicit information on Action Items 1 - 3 | J. Davis | 2015-10-06 | 2015-11-03 | 2016-06-07 | 11/4 - Will review at next meeting 12/1 - Will review during next meeting 1/5 - Reviewed during meeting and will continue to review next meeting 2/1/16 - Created Action Item16 for Western Interconnection feedback 6/7/16 - Through completing Action Items 1 - 3, BPS determined informal comments are not needed. The documentation will be forwarded to the OASIS Subcommittee.
13 | Closed | Create document for responding to AP Item 3.a.i.3 regarding redispatch options which are available through system impact studies | N. Saini | 2015-12-01 | 2016-01-05 | 2016-02-02 | 1/5/16 - Reviewed initial document and will further review during the next meeting 2/2/16 - BPS agreed to forward work paper for review by OASIS Subcommittee
14 | Closed | Create examples for discussing limiting transmission elements to be posted on OASIS for short-term firm reservations | P. Graves R. Robinson | 2015-12-01 | 2016-01-05 | 2016-01-05 | 2/2/16 - Discussed during previous meeting and issue resolved
15 | Closed | Finalize document for AP Item 2.a.ii.2 | N. Saini | 2015-12-01 | 2016-01-05 | 2016-01-05 | 1/5 - The revised document was reviewed and revised and BPS decided to forward to OASIS
16 | Closed | Develop a draft list of additional information to address AP Item 2.a.ii.1 for the Western Interconnect | B. Fung | 2016-02-02 | 2016-03-01 | 2016-05-03 | 5/3/16 - Subcommittee reviewed work paper provided by B. Fung